An Industrial Training/Internship (AIM 4170) Execution Methodology on

Claims Auto-Adjudication Engine for Health Insurance

Carried out at Niva Bupa Health Insurance Company Limited, Gurugram

Submitted to Manipal University Jaipur

Towards the partial fulfilment for the Award of the Degree of

B. Tech Computer Science and Engineering (Artificial Intelligence and Machine Learning)

In Computer Science and Engineering (AIML)

2026-2027

By

Manvik Talwar – 23FE10CAI00130

Under the guidance of

Dr. Noopur Tyagi

Department of Artificial Intelligence and Machine Learning

Manipal University Jaipur

Jaipur, Rajasthan

CONTENTS

1. Introduction	1

2. Methodology at a Glance	1

3. Requirement Analysis and Planning	2

3.1 Sources of Requirements	2

3.2 From Clause to Rule	2

3.3 Scope Definition	3

3.4 Planning	3

4. Phase-wise Execution	3

5. Week-by-Week Log	4

6. Development Workflow	5

6.1 The Per-Rule Loop	5

6.2 Working Practice	6

7. Tools and Environment	6

8. Verification and Validation	6

9. Risk Management	7

10. Communication and Review	7

11. Outcomes against Objectives	8

11.1 Reflection on the Methodology	8

# 1. Introduction

This document describes how the internship project was executed: how requirements were gathered and analysed, how the work was planned and divided into phases, what was done each week, how quality was assured and risks were handled, and how progress was reviewed. The design and implementation of the system itself are described in the accompanying training report.

The project was a claims auto-adjudication engine for Niva Bupa's ReAssure 3.0 health insurance product. Given a claim line item and the policy, member and benefit data, the engine decides whether to approve, partially approve, reject or refer the claim to a human reviewer, computes the payable amount, and records the reasoning behind every step. Deterministic rules handle eligibility and money; a large language model (LLM) is used only to interpret clinical text.

Table 1: Internship details

| Item | Details |
| --- | --- |
| Student | Manvik Talwar (23FE10CAI00130), B.Tech CSE (AIML), 7th semester |
| Course | Industrial Training/Internship (AIM 4170), 2026-2027 |
| Organisation | Niva Bupa Health Insurance Company Limited, Gurugram head office |
| Team | IT Applications |
| Duration | 20 May 2026 to 20 July 2026 (9 weeks) |
| Reporting managers | Sudhanshu Jain, Rajat Gupta |
| Faculty supervisor | Dr. Noopur Tyagi, Department of AIML, MUJ |
| Nature of work | Solo project: analysis, design, implementation, testing and documentation |

# 2. Methodology at a Glance

The work followed an iterative, incremental and specification-driven model. The specification (the policy wording and the technical solution design) was fixed at the start; the system was then built in phases, each adding one capability on top of a working, tested base. Each phase had a defined exit check before the next began.

Table 2: Key methodological choices

| Aspect | Choice | Reason |
| --- | --- | --- |
| Life-cycle model | Iterative and incremental, phase-gated | Each phase ends in a working system; problems surface early rather than at integration |
| Requirements | Specification-driven: policy wording and technical solution design | Insurance decisions must follow the contract exactly; the documents are the source of truth |
| Order of building | Deterministic engine first, AI second | Exact logic was proven before any AI was added, so the AI could never hide a logic error |
| Rules | Encoded as versioned data (rule blueprints), not hard-coded | Product changes become data changes; rules are reviewable by non-programmers |
| Use of AI | LLM only for clinical language, with validated output and human fallback | LLMs can be wrong with confidence; money and eligibility must be exact |
| Quality | Unit, property-based, scenario, API and end-to-end tests | Different defect types need different kinds of test |
| Debugging | Trace-driven: read every decision trace and reasoning log | Most defects showed up as wrong reasoning, not failed assertions |
| Version control | Git with separate stable and working branches | Safe experimentation and a traceable history |
| Documentation | Written alongside the code at each phase | Handover-ready at the end of the internship |

# 3. Requirement Analysis and Planning

## 3.1 Sources of Requirements

Table 3: Requirement sources studied before coding

| Source | What it contained | How it was used |
| --- | --- | --- |
| ReAssure 3.0 policy wording | 2,600+ lines: covers, exclusions, waiting periods, room-rent and co-payment clauses, annexures | Ground truth for every rule and formula |
| Technical solution design (27 May 2026) | Gate sequence, tool contracts, state model, confidence routing, error handling | Architecture and execution order |
| Product and policy rules extraction | 92 rule blueprints, rate tables, mutual-exclusivity constraints | Loaded as the product memory |
| Product and policy API specification | Shapes of the 8 upstream data APIs | Context builder and simulated gateways |

## 3.2 From Clause to Rule

Each clause of the policy wording was analysed and converted into a rule blueprint: an identifier, the gate it belongs to, whether it is deterministic, semantic (needs language understanding) or hybrid, the variants it applies to, the rules it depends on, the calculator it needs, and for semantic rules a prompt that states the rule and its exceptions. Clauses with exceptions received the most attention, because that is where both people and simple keyword matching go wrong (for example, cosmetic surgery is excluded unless it is reconstruction after an accident, burns or cancer).

## 3.3 Scope Definition

The scope was fixed early to the product, policy and member validation layer: the engine receives line items already extracted from bills and medical documents and returns a decision per line item. The Policy Administration System remains the final authority that pays. Fraud analytics, hospital tariffs and upstream extraction were kept out of scope; a document-upload feature was added only to demonstrate field extraction.

## 3.4 Planning

The work was split into phases with an exit check for each (Section 4). The plan was deliberately ordered so that every phase depended only on phases already verified: data models before calculators, calculators before the pipeline, the deterministic pipeline before the AI layer, the engine before the API and user interface.

# 4. Phase-wise Execution

Table 4 summarises each phase and Table 5 shows when each phase ran. Phases overlapped slightly, because the first activities of a phase usually began as the previous phase was being closed.

Table 4: Phases, activities and exit checks

| Phase | Main activities | Output | Exit check |
| --- | --- | --- | --- |
| 0. Domain study and planning | Onboarding in IT Applications; study of the claims process, policy wording and technical solution design; rule inventory; project plan | Rule inventory, phase plan, project structure | Open questions on the wording resolved with reporting managers |
| 1. Deterministic core | Pydantic data models; eight calculators (waiting period, pro-rata, co-pay, deductible, SI waterfall, Lock the Clock, Booster+, pre/post window); seven-gate sequential pipeline; developer front end | Working deterministic engine | Numbers for sample claims checked by hand; calculator unit tests pass |
| 2. AI layer | Product memory loading the rule blueprints; DAG planner with topological sort; semantic agent on a local LLM; four-tier confidence routing | Engine that plans per claim and reads clinical text | Component-by-component compliance check against the design document |
| 3. Hardening and observability | Agent reasoning logger; JSONL telemetry; property-based tests; interactive decision-graph export | Full audit trail; invariant tests | Every LLM call and rule result traceable; invariants hold over random inputs |
| 4. Integration and data layer | Context builder for 8 gateway APIs and simulated gateways; PostgreSQL schema, Alembic migrations, Docker Compose | Claim context assembled from APIs; persistent state | Claim assembled and adjudicated end to end |
| 5. Product user interface | Design system; React console; live Server-Sent Events stream; OCR document extraction; AI decision summaries | Demonstrable console | Ten scenario presets run from the UI |
| 6. Refactor and documentation | Pipeline split into gate modules (execution, financials, state, validation); multi-line claims; endorsements; technical specification | Maintainable code base; specification document | Same results as before the refactor (regression suite) |
| 7. Lifetime state and handover | ReAssure Forever state machine; financial validation; architecture and handover document | Handover package | Handover document reviewed |
| 8. Final hardening (before submission) | Cloud LLM integration (Groq); batched LLM screening; end-to-end scenario testing on the live LLM; defect fixes; report | 77 tests; 10 live scenarios | All tests pass; all scenarios match the deterministic results |

Table 5: Gantt chart of the phases

| Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0. Domain study and planning |  |  |  |  |  |  |  |  |  |  |
| 1. Deterministic core |  |  |  |  |  |  |  |  |  |  |
| 2. AI layer |  |  |  |  |  |  |  |  |  |  |
| 3. Hardening and observability |  |  |  |  |  |  |  |  |  |  |
| 4. Integration and data layer |  |  |  |  |  |  |  |  |  |  |
| 5. Product user interface |  |  |  |  |  |  |  |  |  |  |
| 6. Refactor and documentation |  |  |  |  |  |  |  |  |  |  |
| 7. Lifetime state and handover |  |  |  |  |  |  |  |  |  |  |
| 8. Final hardening |  |  |  |  |  |  |  |  |  |  |

W1 = 20–26 May 2026 … W9 = 15–20 Jul 2026; Oct = final hardening before submission.

# 5. Week-by-Week Log

Table 6 records what was done in each week of the internship and what it produced. Dates of commits and documents in the project repository are given in parentheses.

Table 6: Weekly log

| Week | Dates | Work done | Output |
| --- | --- | --- | --- |
| W1 | 20–26 May | Joined the IT Applications team at the Gurugram head office. Studied the health claims process and the ReAssure 3.0 product: variants, optional covers, Booster+, ReAssure Forever, Lock the Clock. | Domain notes; list of open questions |
| W2 | 27 May–2 Jun | Studied the technical solution design (dated 27 May) and the policy wording clause by clause; reviewed the rule extraction and mapped every rule to a gate; planned the phases; designed the data models and the project structure. | Rule-to-gate mapping; project structure document (2 Jun) |
| W3 | 3–9 Jun | Set up the repository (first commit 3 Jun) with schemas, calculators, the seven-gate pipeline, product memory, planner and a first semantic agent. Built a developer front end connected to the API (5 Jun); wrote the first architecture document; added the agent reasoning logger (8 Jun). | Working deterministic engine; developer UI; architecture draft |
| W4 | 10–16 Jun | Checked the implementation against every section of the design document (compliance report, 10 Jun); added property-based tests; added telemetry; built the context builder and simulated gateway APIs (12 Jun); reorganised the code base. | Compliance report; invariant tests; integration layer |
| W5 | 17–23 Jun | Added interactive decision-graph export and debugging aids (17 Jun); ran the scenario claims end to end and fixed issues found by reading the traces. | Decision graphs; scenario runs |
| W6 | 24–30 Jun | Integrated the API specification for the eight data sources; added PostgreSQL with Alembic migrations and Docker Compose (26 Jun); defined the design system and the console layout (30 Jun). | Database layer; design system |
| W7 | 1–7 Jul | Restructured the product memory layer (2 Jul); added OCR-based document extraction (2 Jul); built the live streaming console and its state management (6 Jul); updated the architecture document. | Streaming console; document upload |
| W8 | 8–14 Jul | Refactored the pipeline into separate gate modules (14 Jul); added multi-line claims and endorsement handling; wrote the technical specification document (14 Jul). | Modular pipeline; technical specification |
| W9 | 15–20 Jul | Implemented the ReAssure Forever state machine and financial validation (16 Jul); wrote the architecture and handover document (16 Jul); handed over the project. | Handover document |
| Final | Oct 2026 | Before submission: integrated the Groq cloud LLM, batched exclusion screening to stay within free-tier limits, ran all ten scenarios on the live LLM, fixed the defects found, and wrote the report. | 77 passing tests; report, presentation |

# 6. Development Workflow

## 6.1 The Per-Rule Loop

Every rule went through the same five steps. Repeating one loop for 92 rules kept the work consistent and made progress easy to measure (rules implemented and tested out of the total).

- Analyse the clause in the policy wording, including its exceptions and cross-references.

- Encode it as a rule blueprint: gate, execution type, dependencies, applicable variants, calculator or prompt.

- Implement the gate check or calculator, keeping calculators pure functions so they are easy to test.

- Test it: a unit test; for money, a property-based test; and a scenario preset that exercises it.

- Read the trace: run the scenario and read the decision trace and LLM reasoning log line by line; fix and repeat.

## 6.2 Working Practice

- Work was committed to Git in small steps, with a stable branch and a working branch.

- The full test suite was run before each commit; it runs offline in about 30 seconds because a deterministic responder stands in for the LLM.

- Questions about the meaning of a clause were collected and resolved with the reporting managers rather than guessed.

- Documentation (architecture, compliance report, specification, handover) was updated at the end of the phase it described.

# 7. Tools and Environment

Table 7: Tools used during execution

| Purpose | Tools |
| --- | --- |
| Language and validation | Python 3.12, Pydantic v2, pydantic-settings |
| Service layer | FastAPI, Uvicorn, asyncio, Server-Sent Events |
| AI | Local LLM through llama.cpp (Gemma 4); Groq API (Qwen3.8 27B) |
| Documents | pypdf, Tesseract OCR, Pillow |
| Data | PostgreSQL 16, SQLAlchemy 2 (async), Alembic, Docker Compose, pgAdmin |
| User interface | React 19, TypeScript, Vite, Tailwind CSS |
| Testing | pytest, Hypothesis, FastAPI TestClient, Playwright |
| Engineering | Git and GitHub, VS Code, uv |

# 8. Verification and Validation

Verification checked that each part was built correctly; validation checked that the whole system made the right decisions on realistic claims.

Table 8: Verification and validation activities

| Level | What was checked | Result |
| --- | --- | --- |
| Unit | Each calculator and gate against hand-worked examples | Pass |
| Property-based | Money conserved; ratios bounded; pools never negative; deductible within limit | Pass over thousands of random inputs |
| Scenario | Complete claims through the pipeline against expected outcomes | Pass |
| API and provider | Endpoints, streaming, LLM provider, batching and fallback | Pass |
| Compliance | Each component against each section of the design document | Gaps recorded (e.g. PAS reconciliation is a stub) |
| End to end | Ten scenario presets through the real UI on the live LLM | 10/10 complete; decisions match the deterministic mode |

In total 77 automated tests pass. End-to-end testing in the final phase found defects that unit tests had missed, including a room-rent deduction that could exceed the claimed amount and a request for human review that was being lost; each fix came with a regression test that fails on the old code.

# 9. Risk Management

Table 9: Risks identified and how they were handled

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Misreading a policy clause | Wrong decisions on real claims | Clause-by-clause analysis; exceptions written into rules; questions resolved with reporting managers |
| LLM gives a confident wrong answer | Wrong exclusion or approval | LLM only for language; schema-validated output; confidence thresholds; human review on any doubt |
| Arithmetic errors in money | Over- or under-payment | Deterministic calculators; property-based tests of invariants |
| Cloud LLM rate limits or outages | Slow or failed adjudication | Batched screening (one call per line item); failures route to review; offline mode for demonstrations |
| Sensitive health data | Privacy exposure | Simulated data during development; local-model option for production; minimal fields in prompts |
| Concurrency bugs | Inconsistent state between claims | Per-claim and thread-local state; row locks on balances |
| Scope creep | Unfinished core | Scope fixed to the validation layer; extras (document upload) kept optional |

# 10. Communication and Review

Progress and open questions were reviewed with the reporting managers, Sudhanshu Jain and Rajat Gupta, who explained the claims domain, clarified the policy wording and reviewed design decisions. Written artefacts were produced at the end of the phases they describe, so the state of the project was always documented:

Table 10: Documents produced during the internship

| Document | When | Purpose |
| --- | --- | --- |
| Project structure | 2 Jun | Planned modules and phase boundaries |
| Architecture document | 5 Jun, updated to 6 Jul | System design reference |
| Compliance report | 10 Jun | Implementation checked against the design document |
| Design system | 30 Jun | Consistent user interface |
| Technical specification | 14 Jul | Detailed specification of the engine |
| Architecture and handover document | 16 Jul | Handover to the team |
| Training report, presentation | Oct 2026 | Academic submission |

# 11. Outcomes against Objectives

Table 11: Objectives and how they were met

| Objective | Outcome |
| --- | --- |
| Encode the product rules as data | 92 rule blueprints in a versioned product memory |
| Exact money | Deterministic calculators with property-based tests |
| LLM only for language | Semantic agent with validated JSON output; batched screening |
| Safe routing | Four-tier confidence routing; data gaps and errors go to human review |
| Complete audit trail | Decision trace, tool calls, LLM prompts and replies, telemetry, decision graphs |
| Usable product | Streaming API and React console; cloud, local and offline LLM modes |
| Thorough testing | 77 automated tests; 10 scenarios on the live LLM |

## 11.1 Reflection on the Methodology

Building the deterministic engine before adding AI was the most valuable decision: it gave a trusted baseline, and in the end the live-LLM results matched it on every scenario. Reading traces end to end found more defects than assertions did. If I repeated the project, I would build a labelled evaluation set from historical claims at the start, so that every change could be measured as agreement with human decisions, and I would add end-to-end scenario runs to the routine of every phase rather than mainly at the end.